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In attendance: Egbert Smit, Andrew Craven, Mark Hope-Jones, Margaret Davies, Bill Bloxsome
Apologies: Christine Bates 

Budget

· Andrew completing ‘end of grant’ award. Andrew will return unused funds and reapply, using quotes from Bill.

· After Reg 14 we go through representations (comments) and amend the plan if necessary. A Basic Conditions Statement would be around £400 from Bill, and a Consultation Statement about £400 from Chris.

· Then comes Reg 16 – six weeks of consultation, perhaps more comments and we may need to respond to them. Then it goes to the examiner, who may have questions we need Bill’s help with, and we may need to amend the plan again.

· Any allocated sites (probably Clifford village only) will need a Site Assessment and Bill can quote on this.

· Bill would also do a final read-through and edit of the completed plan, for consistency and planning-friendly lingo.

Views

· Once we have a list, we can mark them on a map and take photographs. It would make sense to order base maps of CV and PW from Hoople – Emma Noble, the Parish Clerk, could order these, perhaps via Christine. We think we already have one for the whole parish.

· An OS license number needs to be included on all maps. Christine can provide this.

· Margaret and Andrew will email to the group a list of the views they noted. Mark will compile a combined list.

· It might be nice to do a group walk of the Wye Valley Walk and see if there any other important views.

Housing

· For CV and PW, we do a SB (with justification) for each. We also need to define…

1.) A set of criteria for development within each SB (scale, character, etc.) 
2.) A set of criteria for allocated sites, informed by site assessments (e.g. important trees, hedgerows, access, variety of housing).
3.) A policy for sustainable design. Bill will provide an example.
4.) A policy enabling community housing. Bill will look for an example, based on Herefordshire policy H2 (affordable housing).

· We already have criteria for site assessment. 

· We should include a ‘rural windfall allowance’ based on evidence (past trends and future potential). Might be around 5 until 2031.

Priory Wood

· Central area to be excluded from SB but parts of it defined as local green space.

· Probably best not to have allocated sites in PW, as even the biggest plot only has three properties.

· In defining the SB, we should mention views through the green spaces. For example, views to Wye Valley from southerly road, giving a sense of Priory Wood being on a ridge. This section of road is part of the Wye Valley Walk.

· Mark will write up the wording for PW.

Clifford village

· One site came forward after the call for sites (Emma). There will be other allocated sites. Andrew is in touch with Chuff and Candia.

· We could say that we have evaluated 3 sites, with 3 other potential small infill sites. We would rank the sites we evaluate 1, 2, 3, according to the criteria. The growth provisions would likely be met with the first 2.

· Andrew will write up the wording for CV.
